## Sheet1
Product Backlog sample for Social media application
ID | Title | Epic | User Story | Priority (MoSCoW) | Status | Acceptance Criteria | Functional Requirements | Non-Functional Requirements | Original Estimate | Actual Effort (In days)
1 | Jira Requirement Extraction | Requirement Intelligence | As a QA engineer, I want the system to automatically fetch Jira ticket details so that test cases are generated based on updated requirements. | Must | In Progress | 1. Jira ticket is fetched using ticket ID. 2. Summary and description are extracted. 3. Acceptance criteria are parsed. 4. Figma links (if present) are identified. | 1. Jira API integration 2. Requirement parsing engine 3. Structured data output | 1. Response time < 3 seconds 2. Secure authentication 3. Error handling for invalid tickets | 6 days | 4 days
2 | Figma Design Analysis | Requirement Intelligence | As a QA engineer, I want the system to analyze Figma designs linked in Jira so that UI-related test cases are accurately generated. | Must | Pending | 1. Extract Figma file ID from Jira. 2. Download design frames/screens. 3. Identify UI elements from design. 4. Provide structured UI insights to AI. | 1. Figma API integration 2. PNG export handling 3. UI element mapping | 1. Secure API token handling 2.Design parsing < 10 seconds 3. Scalable for multiple screens | 7 days
3 | AI Test Case Gap Analysis | Test Case Intelligence | As a QA engineer, I want AI to compare requirements with existing test cases so that missing, modified, or obsolete test cases are identified. | Must | Backlog | 1. Compare new requirements with existing test cases. 2. Categorize as New / Modify / Remove / Maintain. 3. Avoid duplicate test cases. 4. Present structured output. | 1. TCMS integration 2. LLM-based semantic comparison 3.Categorization logic | 1. AI response < 10 seconds ≥85% classification accuracy 2. Maintain audit logs | 7 days
4 | Human Approval Workflow | Governance | As a QA lead, I want to review and approve AI-generated test case changes so that incorrect automation is avoided. | Must | Pending | 1. Display AI suggestions clearly. 2. Allow edit/delete/approve actions. 3. Approved cases update TCMS. 4. Track version history. | 1. Review UI 2. Google Sheets/TCMS update integration 3.Version tracking | 1. Secure access control 2. Approval update < 2 seconds 3. High usability | 7 days
5 | MCP Device Selection & Connection | Test Execution | As a tester, I want to select Android or iOS devices through MCP so that testing can run on real devices or simulators. | Must | In Testing | 1. List available devices. 2. Select specific device. 3. Establish connection successfully. 4. Handle connection failures. | 1. Android ADB integration 2.iOS Simulator integration 3. Device abstraction layer | 1.Device connection < 5 seconds 2. Stable session handling 3. Cross-platform support | 7 days
6 | AI-Assisted Manual Testing Execution | Test Execution | As a tester, I want AI to navigate the mobile app and validate UI elements so that manual testing effort is reduced. | Should | Backlog | 1. Launch app via MCP. 2. Extract XML screen structure. 3. Perform tap/swipe/type actions. 4. Log execution steps. | 1. XML hierarchy parsing 2. Tap by text functionality 3. Screen size detection | 1. Command execution < 2 seconds 2. Stable automation flow 3. Reliable error reporting | 8 days
7 | Test Steps Auto-Generation | Test Case Intelligence | As a QA engineer, I want AI to automatically generate detailed manual test steps for incomplete test cases so that documentation is standardized. | Must | Pending | 1. Detect blank test steps in sheet. 2. Generate structured steps. 3. Follow predefined guidelines. 4. Update sheet automatically after approval. | 1. Google Sheets read/write integration 2. Guideline-based generation 3. Structured step formatting | 1. Generation time < 8 seconds 2. High clarity and readability 3. No data loss | 6 days
8 | CI/CD Pipeline Integration | Continuous Testing | As a DevOps engineer, I want automation scripts to execute automatically during builds so that quality checks are continuous. | Could | Backlog | 1.Scripts trigger on code commit. 2. Reports generated after execution. 3.Failure notifications sent. 4. Logs stored centrally. | 1. GitHub Actions/Jenkins integration 2. Report generation module 3. Alert notification system | 1. Minimal pipeline delay 2. Scalable execution 3. High reliability | 8 days
9 | Automation Script Generation | Test Automation | As an automation engineer, I want AI to generate automation scripts from approved test cases so that regression testing is accelerated. | Must | Backlog | 1. Convert manual test case to script. 2. Include valid locators & assertions. 3. Follow automation framework standards. 4. Allow manual script refinement. | 1. LLM-based script generation 2. Framework template integration 3. Code export to repository | 1. Script generation < 15 seconds 2. 90% syntactically correct scripts 3. Maintain coding standards | 6 days
10 | Multi-LLM Intelligent Orchestration | AI Intelligence Layer | As a system architect, I want to integrate multiple LLMs (Claude, Gemini, ChatGPT) so that test case reasoning accuracy is improved. | Could | Backlog | 1. System supports switching between LLMs. 2. Compare outputs for consistency. 3. Fallback to alternate LLM on failure. 4. Log AI reasoning decisions. | 1. API integration with multiple LLMs 2. Response comparison logic 3. Error fallback mechanism | 1. Secure API key management 2. Response time optimization 3. High availability | 7 days