## Sheet1
Product Backlog sample for Social media application
ID | Title | Epic | User Story | Priority (MoSCoW) | Status | Acceptance Criteria | Functional Requirements | Non-Functional Requirements | Original Estimate | Actual Effort (In days)
1 | Jira Requirement Extraction | Requirement Intelligence | As a QA engineer, I want to enter a Dev Done Jira ID so that the system automatically fetches requirement details and attached design files. | Must | In Progress | 1. System accepts valid Jira ID input. 2. Jira summary and description are fetched successfully. 3. Attached Figma design links are detected. 4.Error displayed for invalid Jira ID. | 1. Integrate with Jira REST API. 2. Parse description and attachments. 3. Validate Jira status as “Dev Done”. | 1. API response time < 3 seconds. 2. Secure API authentication. | 5 days | 4 days
2 | Existing Test Case Retrieval | TCMS Integration | As a QA engineer, I want the system to fetch existing test cases from TCMS so that duplication is avoided. | Must | Pending | 1. TCMS API connection established. 2. Test cases retrieved based on Jira reference. 3. Folder/project mapping supported. | 1. Secure TCMS API integration. 2. Fetch title, steps, metadata.. | 1. Data consistency maintained. 2. Retrieval time < 5 seconds. | 5 days | 5 Days
3 | AI Test Case Classification | Intelligent Test Case Evolution | As a QA lead, I want the system to classify test cases as New, Modify, or Remove so that regression suite remains updated and clean. | Must | Backlog | 1. AI compares requirement with existing cases. 2. Each case labeled correctly. 3. Classification summary displayed. | 1. LLM-based comparison logic. 2. Structured output format. | 1. Accuracy > 80%. 2. Deterministic structured response. | 7 days
4 | Approval Dashboard | Governance Workflow | As a QA lead, I want an approval screen displaying new, modified, and removed test cases so that I can validate before updating TCMS. | Must | Backlog | 1. Categorized test cases displayed. 2. Edit/Approve/Reject options available. 3.Approval logs stored. | 1. UI dashboard for review. 2. Store approval decisions. | 1. Role-based access control. 2. Audit trail enabled. | 7 days
5 | TCMS Update Automation | Repository Synchronization | As a QA engineer, I want approved test cases to be automatically updated in TCMS so that documentation remains synchronized. | Must | Backlog | 1. New cases created. 2. Modified cases updated. 3. Removed cases excluded. 4. Update confirmation shown. | 1. TCMS write API integration. 2. Status update handling. | 1. Transaction reliability. 2.Data integrity maintained. | 5days
6 | Mobile Test Execution | Execution Engine | As an automation engineer, I want the system to execute approved test cases in the mobile application so that regression validation is automated. | Should | Backlog | 1. Device selection supported. 2. App launches successfully. 3. Test steps executed via tap/swipe/input. 4. Execution logs generated. | 1. Mobile automation inegration. 2. MCP tool orchestration. | 1. Execution stability > 95%. 2. Log generation for traceability. | 5days
7 | Automation Script Generation | Automation Bridge | As an automation engineer, I want scripts to be generated from validated test cases so that they are ready for CI/CD integration. | Could | Backlog | 1. Script follows structured format (POM). 2. Compatible with automation framework. 3. Export option available. | 1. Script template engine. 2. Mapping manual steps to automation commands. | 1. CI/CD compatibility. 2. Maintainable code structure. | 5days
8 | Role-Based Access Control | System Governance & Security | As a QA Lead, I want role-based login and access control so that only authorized users can approve or modify test cases. | Must | Backlog | 1. Users must log in before accessing the system. 2. Role types defined (QA Engineer, QA Lead, Automation Engineer). 3. Only QA Lead can approve/reject test cases. 4. Unauthorized access is restricted. | 1. Authentication module implementation. 2. Role-based permission mapping. 3. Secure session management. | 1. Secure password storage (hashing). 2. Response time for login < 2 seconds. 3. Protection against unauthorized access. | 5days
9 | Workflow Logging & Audit Trail | Monitoring & Transparency | As a Scrum Master, I want complete lifecycle logs so that QA activities can be tracked and audited. | Should | Backlog | 1.All lifecycle actions are logged (fetch, generate, approve, update, execute). 2.Logs include timestamp and user details. 3. Logs are retrievable for review. | 1. Centralized logging mechanism. 2. Store action history in database. 3. Provide log viewing interface. | 1. Logs must not impact performance. 2. Data retention policy defined. 3.Secure log storage. | 5days
10 | Error Handling & Retry Mechanism | System Reliability | As a QA Engineer, I want the system to handle API failures and retry operations so that workflow is not interrupted. | Should | Backlog | 1. API failures display meaningful error messages. 2. Retry mechanism implemented for TCMS updates. 3 System does not crash on external API failure. 4. Failure events are logged. | 1. Exception handling module. 2. Retry logic for failed operations. 3. User notification system. | 1. System uptime > 95%. 2. Failure recovery within acceptable time. 3. No data corruption during retry. | 5days